## Sheet1
Name | Time (Hours) | Task | Date | Completed | Notes
Ben | 2 | Create Delivery Repository | 2023-09-04 | No | Task Has H2 Console working but sql migration failed
Ben | 0.5 | Finished Create Delivery Repository | 2023-09-05 | Yes | Fixed SQL migration
Ben | 1 | Create Flyway Database | 2023-09-07 | No | Create commands finished but issues existing
Tyler | 1 | Setup Inital Cart MVC pattern | 2023-09-07 | no | Setup proper sql commands when schema is made
Tyler | 1 | Setup Initial Product MVC pattern | 2023-09-07 | no | Setup proper sql commands when schema is made
Jamie | 2.5 | Created Landing Page | 2023-09-07 | yes | Does not have any functional programming
Ben | 2 | Create Flyway Database | 2023-09-08 | Yes | Fixed SQL migraiton issues
Ben | 0.25 | Updated DB Schema to match Flyway | 2023-09-08 | Yes
Ben | 0.5 | Fixed Flyway Database Issue | 2023-09-08 | Yes | Incorrect Name For 1 Table
Kiran | 3 | Created search results page | 2023-09-08 | yes | Does not have any functional programming
Jamie | 1.5 | Created Product page | 2023-09-10 | yes | Does not have any functional programming
Kiran | 0.5 | Modified naviagtion bar to add search bar | 2023-09-11 | yes
Tyler | 0.5 | finalized schema setup for cart and product | 2023-09-12 | yes
Tyler | 0.5 | Implemented RemoveItemFromCart | 2023-09-12 | yes | may need to return once products have been added to the database to ensure it works
Tyler | 0.25 | Implemented addItemToCart | 2023-09-12 | yes | may need to return once products have been added to the database to ensure it works
Tyler | 1 | Incremental increase and decrease functionality added | 2023-09-12 | yes | may need to return once products have been added to the database to ensure it works
Kiran | 2.5 | Created cart page | 2023-09-13 | yes | Does not have any functional programming
Tyler | 1 | Wrote tests for Cart functionality | 2023-09-14 | yes
Ben | 2 | Created the CRUD functionality for Delivery Repository | 2023-09-14 | Yes | Additionaly functionality for the deliveries still required
Ben | 1 | Added return for the deliveries contents | 2023-09-14 | Yes | Added the functionality for delvieries that was missing
Andy | 3 | Created Practice Database | 2023-09-14 | Yes
Ben | 3 | Create Product Repo | 2023-09-15 | Yes | Also fixed several cart tests
Peter | 4 | added frontend for user profile and checkout | 2023-09-15 | Yes
Peter | 3 | implemented tests and started crud functionality for notifications | 2023-09-15 | no | need to impliment services and controller
Ben | 3 | Created Product Search | 2023-09-15 | Yes
Peter | 2 | finisheed controller and services for notifications | 2023-09-16 | yes | may need to test
Andy | 2.5 | Implementing Continous Integration with GitHub Actions | 2023-09-16 | No