## Sprint-2 Burndown
Sprint 2: Burndown Chart
Backlog ID | Tasks | Initial Estimate | 2018-09-01 | 2019-09-01 | 2020-09-01 | 2021-09-01 | 2022-09-01 | 2025-09-01 | 2026-09-01 | 2027-09-01 | 2028-09-01 | 2029-09-01 | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
23 | Create User Repository | Day 0: 2; Day 3: 3
33 | Create notifications icon | bar: Day 0
35 | Search Term Capture from UI | Day 0: 4; Day 8: 5
38 | Add filter menu | Day 0: 1; Day 13: 2
39 | Implement adding item to favourites | Day 0: 1; Day 7: 1.5
40 | Add filter functionality | Day 0: 3; Day 14: 2
43 | Implement adding a new account to database | Day 0: 3; Day 7: 3
45 | Image for item linked to product page | Day 0: 5; Day 4: 2
46 | Implement notification functionality for website | Day 0: 4
47 | Cart price calculation implemented | Day 0: 1; Day 15: 3
75 | User login | Day 0: 3; Day 3: 1; Day 4: 2; Day 5: 2; Day 6: 1; Day 7: 5; Day 8: 7
76 | Connecting backend to search page | Day 0: 5; Day 1: -12.5; Day 2: 3; Day 3: 3; Day 4: 5; Day 7: 2
77 | Connecting backend to product page | Day 0: 3; Day 5: -14; Day 6: 4; Day 7: 2; Day 9: 5
78 | Connect backend to user profile page | Day 0: 2; Day 15: 2
79 | Connecting backend to notifications page | Day 0: 2
80 | Connecting backend to cart page | Day 0: 4; Day 10: -24; Day 11: 6; Day 12: 3; Day 13: 5; Day 14: 8; Day 15: 7
81 | Port test data into database | bar: Day 0; Day 4
Remaining Effort |  | 45 | 57.5 | 54.5 | 47.5 | 37.5 | 49.5 | 44.5 | 31 | 19 | 14 | 38 | 32 | 29 | 22 | 12 | 0
Ideal Trend |  | 45 | 42 | 39 | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Sprint-1 Burndown
Sprint 1: Burndown Chart
Backlog ID | Tasks | Initial Estimate | 2021-08-01 | 2022-08-01 | 2023-08-01 | 2024-08-01 | 2025-08-01 | 2004-09-01 | 2005-09-01 | 2006-09-01 | 2007-09-01 | 2008-09-01 | 2011-09-01 | 2012-09-01 | 2013-09-01 | 2014-09-01 | 2015-09-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
22 | Create Product Repository | Day 0: 2; Day 9: 1; Day 15: 3
24 | Basic Delivery Functionality | Day 0: 2; Day 6: 2; Day 7: 0.5; Day 14: 2
25 | Create Cart Repository | Day 0: 2; Day 9: 1
26 | Create Notification Repository | Day 0: 2; Day 15: 5
27 | Create Home Page | Day 0: 1.5; Day 9: 2.5; Day 11: 0.5
28 | Create product page | Day 0: 1; Day 11: 1.5
29 | Create cart page | Day 0: 1; Day 13: 2.5
30 | Create user profile page | Day 0: 1; Day 15: 2
31 | Create checkout page | Day 0: 1; Day 15: 2
32 | Create search results page | Day 0: 1; Day 10: 3
34 | Develop product categories | Day 0: 1; Day 14: 1.5
37 | Search Querying | Day 0: 3; Day 15: 1.5
41 | Implement increase quantity functionality for cart | Day 0: 1.5; Day 12: 0.5
42 | Implement decrease quantity functionality for cart | Day 0: 1.5; Day 12: 0.5
44 | Implement remove item functionality for cart | Day 0: 1.5; Day 12: 0.5
48 | Add To Cart functionality for result page added | Day 0: 1; Day 12: 0.25
49 | Add Item To Cart functionality for product page added | bar: Day 0; Day 14
50 | Linked product database to search functionality | Day 0: 3; Day 15: 1.5
51 | Database data queried for product page | Day 0: 5; Day 12: 0.5
52 | Create DB Schema | Day 0: 8; Day 10: 0.25; Day 15: 2.5
53 | Develop Practice Products | Day 0: 4; Day 14: 1.5
56 | Return list of items in deliveries | bar: Day 0; Day 14
57 | Create Flyway migration for database schema | Day 0: 2; Day 9: 1; Day 10: 2.5
Remaining Effort |  | 48 | 48 | 48 | 48 | 48 | 48 | 46 | 45.5 | 45.5 | 40 | 34.25 | 32.25 | 30 | 27.5 | 20.5 | 3
Ideal Trend |  | 48 | 48 | 45 | 42 | 38 | 35 | 32 | 29 | 26 | 22 | 19 | 16 | 13 | 10 | 7 | 3